Project Planning Phase

Project Planning Template

Auto Ticket Classification using Flow Designer

| Date | 15 February 2025 |
| --- | --- |
| Team ID | [Enter Team ID] |
| Project Name | Auto Ticket Classification using Flow Designer |
| Maximum Marks | 5 Marks |

# 1. Product Backlog, Sprint Schedule and Estimation

The backlog below translates the implemented project into Epics and User Stories. Story points follow the Fibonacci-style scale specified in the Planning Logic document.

| Sprint | Functional Requirement (Epic) | User Story No. | User Story / Task | Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Epic 1 – Requirement Analysis | USN-1 | Document business use case and project requirements | 2 | Medium | Vimalraj Arul |
| Sprint-1 | Epic 2 – Platform Configuration | USN-2 | Create Project Update Set and make it current | 1 | Medium | Team Lead |
| Sprint-1 | Epic 2 – Platform Configuration | USN-3 | Create Incident WorkFlow custom table | 3 | High | Bala Chander |
| Sprint-1 | Epic 2 – Platform Configuration | USN-4 | Create fields and configure data types | 3 | High | Bala Chander |
| Sprint-1 | Epic 2 – Platform Configuration | USN-5 | Configure Category/Subcategory dependency | 3 | High | Bala Chander |
| Sprint-2 | Epic 3 – Automation | USN-6 | Create Auto Classify School IT Tickets flow | 5 | High | Murugan R |
| Sprint-2 | Epic 3 – Automation | USN-7 | Configure classification rules for issue types | 3 | High | Murugan R |
| Sprint-2 | Epic 3 – Automation | USN-8 | Configure caller email notification | 2 | Medium | Murugan R |
| Sprint-2 | Epic 4 – Testing | USN-9 | Execute classification and email test scenarios | 5 | High | Vimalraj Arul / Murugan R / Diwan Kumar M |
| Sprint-2 | Epic 5 – Deployment | USN-10 | Complete and export Project Update Set | 2 | Medium | Team Lead |
| Sprint-2 | Epic 6 – Documentation | USN-11 | Prepare documentation, screenshots and project evidence | 3 | High | Team |

# 2. Sprint Tracker

The supplied template requires actual sprint dates and completed points. The source files do not provide your team's actual execution dates, so these fields are intentionally marked for entry rather than invented.

| Sprint | Total Points | Duration | Start (Planned) | End (Planned) | Completed | Release (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 12 | 6 Days | [Enter actual] | [Enter actual] | [Enter actual] | [Enter actual] |
| Sprint-2 | 20 | 6 Days | [Enter actual] | [Enter actual] | [Enter actual] | [Enter actual] |

# 3. Velocity

Using the planned backlog: 32 total story points / 2 planned sprints = 16 story points per sprint. Actual velocity should be recalculated from the completed-points column after the real sprint results are entered.

# 4. Planned Burndown

# 5. Sprint Deliverables

| Sprint | Deliverables | Evidence |
| --- | --- | --- |
| Sprint-1 | Requirements, Update Set, custom table, fields and dependent choices | ServiceNow configuration screenshots |
| Sprint-2 | Flow, classification, email, testing, deployment and documentation | Flow/test/email/Update Set evidence |

# 6. Submission Notes

Story points represent relative effort, not hours.

Enter the team's actual sprint dates before submission.

Enter actual Story Points Completed based on evidence.

Use the actual release date for each sprint.

Do not present the planning baseline as measured historical velocity.